## Tracking _org name_
Task Topic | PRAPARE Detailed Workplan Tasks | Status (Completed, In Progress) | PRAPARE Toolkit Resources | Toolkit Chapters | Estimated Timeframe | Responsible Staff | Progress Description | Lessons Learned | Notes/Solutions/ Needs for Improvement
1. Strategize the Implementation | Complete readiness assessment | Completed
| Implementation interview | Completed
| Understand and assess organizational priorities, feasibiilty, and readiness for implementation. | Completed | Understand PRAPARE full chapter, Implementation Readiness Assessment Tool | 1, 3
| Engage key stakeholders and staff champions | Completed | Engage Key Stakeholders - full chapter | 2
| Form implementation team | Completed | n/a
| Develop KPIs/MOS | In progress | n/a
| Train implementation team |  | n/a
| Understand and develop plans to integrate data collection implementation materials and process including: | In progress | Strategize the Implementation Plan - full chapter | 3
| Plan effective workflow model (part of training 1B) | Completed | Five Rights Framework tool | 3
| Plan evaluation objectives and process (part of training 2C) | In progress | Clinic PDSA samples | 3
| Refine workplan as needed to align with organizational strategy | In progress | Workplan / Progress Report Sample | 3
| Develop plans and processes for using the data for enhanced clinical care, complexity analysis and advocacy for more effective payment |  | Strategize the Implementation and Respond To Your Data - full chapters | 3, 8
2. Integrate EHR template | Refine existing EHR template for clinic(s) needs and workflow and system requirements as needed | In progress | Technical Implementation - full chapter | 4
3. Train Staff | Modify the training material provided as needed (IPCA TtT Modules 1A-3B) |  | Training Curriculum | 5
| Train staff, collect feedback, and adjust as necessary |  | Training Curriculum | 5
4. Implement Data Collection | Develop a data strategy, set goals for data collection and performance improvement |  | Develop a Data Stratey - full chapter | 6
| Roll out implementation |  | Technical Implementation - full chapter | 4
| Document lessons learned and needs for improvement |  | Workplan / Progress Report Sample | 3
| Test and track implementation process using PDSA framework |  | Clinic PDSA samples | 3
5. Report and Act on Data | Document the protocol implementation process, lessons learned, and recommendations for improvement. |  | Clinic PDSA samples, Workplan / Progress Report Sample | 3
| Report data and validate with internal and external stakeholders and local community as appropriate |  | Understand and Evaluate Your Data - full chapter, Sample Data Validation | 7
| Implement clinic quality improvement and population improvement plans based on the data |  | Population Planning Checklist and Samples of Data Use | 6
| Build capacity and respond to needed interventions based on data |  | Build Capacity to Respond to SDH and Respond with Interventions - full chapters | 8 and 9
| Document interventions to address SDH needs |  | Track Enabling Services - full chapter | 10
| Plan for using data for additional research and validation using other clinical/community measures (e.g. health outcomes, costs, community interventions). Document use of the collected data for clinical care, for community partnerships, advocacy or other related efforts. |  | Respond To Your Data full chapter, Samples of Data Use | 9, 6